## Sheet1
ID	Task	As a...	I want to be able to...	So that… /User Story/	Estimation (We can also use Story Points)	Priority	Status	Assigned to
Sprint 1
1	Set up a working environment in Github	developer	access the latest verion of the project at any time	I can contribute to the work of my team in the most efficient and productive way
2	Set up a Dockerfile; use Docker	developer	make efficient use of system resources; enable fast software delivery cycles; ensure application portability	I can work easily in collaboration with the rest of my team
3	Project builds to self-contained JAR with Maven.	developer	have a standard directory structure while working on the project; get package dependencies; aggregate Java class files
4	Use Travis Ci	developer	to build and test the project automatically after "pushing"	I can automate the testing process and debug easily in collaboration
5	Add develop and release branch.	developer	to work on the project independently, introducing new features and working on bugs without affecting the original source code; to work collaboratevly with my team members without affecting their version of the code	I can ensure an effective and flexible process of development
6	First release on GitHub	client	track the progress of the scrum team by seeing if they are able to deliver the necessary to me and my company features	I can give feedback as soon as possibe, ensuring that the software follows the requirements of my company
7	Create Product Backlog	part of the scrum team	to have access to each task that my team is working on; propose new tasks; vote on the relevance and importance of each proposal by discussing it with the other team members	I am aware of what is to be done and take an active part in the solving of any ongoing problems
8	Define Codes of Conduct	part of the scrum team	agree upon a code of conduct	I know I'll be respected and I will work in an ethical environment with well established work habits.
Sprint 2